## dailytasklist
DAILY TASKS
Date | TASKS | STATUS | DUE DATE
2025-10-08 | Install pycharm | ✅ Complete | 2025-10-08
| Install Driver for CUDA | ✅ Complete | 2025-10-08
| Install whisper large-v3 model | ✅ Complete | 2025-10-08
| VisionAI-Audio repo setup: create repo, add structure, Colab notebook, CLI test, sample audio, demo video, push to GitHub | ✅ Complete | 2025-10-08
2025-10-09 | Create repository structure according to task 2 | ✅ Complete | 2025-10-15
| Find 20 audio samples for urdu and english (5 done) | 🏃 In progress | 2025-10-15
| Create model comparison.py and write code for faster_whisper to get metrics in json file | ✅ Complete | 2025-10-15
2025-10-10 | Find 20 audio samples for urdu and english (11 done) | 🏃 In progress | 2025-10-15
| Refactor faster whisper implementation: make it modular | ✅ Complete | 2025-10-15
| Add openai whisper implementation in models/openai_whisper | ✅ Complete | 2025-10-15
| Install the requirements for openai whisper like models, pip etc | ✅ Complete | 2025-10-15
| Refactor model_comparison.py to act as main file to run all the models | ✅ Complete | 2025-10-15
| save the result for faster and openai whisper in json file for evaluation purposes | ✅ Complete | 2025-10-15
2025-10-13 | Find 20 audio samples for urdu and english | ✅ Complete | 2025-10-15
| Add whisper.cpp implementation in models/whisper_cpp | ✅ Complete | 2025-10-15
| Add whisperx implementation in models/whisperx | ✅ Complete | 2025-10-15
| Test both (whisper.cpp and whisperx) with 1 or 2 audio samples | ✅ Complete | 2025-10-15
| Integrate both implementation in model_comparison.py | ✅ Complete | 2025-10-15
2025-10-14 | Implementation of resource_monitor.py to track CPU,GPU, and Memory usage | ✅ Complete | 2025-10-15
| Implementation of metrics_calculator.py to calculate wer/cer | 🏃 In progress | 2025-10-15
| Add preprocessing in of audio whisper_cpp_model.py because it does not support greater then 16kHz and 16bit audio | ✅ Complete | 2025-10-15
| Test all the models with all test_audio_samples and save result in respective json | ✅ Complete | 2025-10-15
| Test metrics_calculator.py by passing prediction(faster-whisper) and reference(openai-whisper) json and save their results | ✅ Complete | 2025-10-15
2025-10-15 | Implementation of metrics_calculator.py to calculate wer/cer | ✅ Complete | 2025-10-15
| create a new py file which combine the results of all models into one combine_summary.json | ✅ Complete | 2025-10-15
| Create model_comparison_analysis.ipynb on colab for visualization | ✅ Complete | 2025-10-15
| Generate different graphs for visualization | ✅ Complete | 2025-10-15
| Update README.md | ✅ Complete | 2025-10-15
| Create model_evaluation.md | ✅ Complete | 2025-10-15
| push all code related to task 2 to github | ✅ Complete | 2025-10-15
| Research about insanely fast whisper | ✅ Complete | 2025-10-15
2025-10-16 | Understand requirements for task 3 | ✅ Complete | 2025-10-22
| Find 10-15 test audio's for task 3 | ✅ Complete | 2025-10-22
| Create a notebook for task 3 called task3_fasterWhisper_optimization.ipynb | ✅ Complete | 2025-10-22
| Section 1 of the notebook Set Up and Load Data: Import necessary libraries and set up the environment. Load sample audio files for testing, including noisy, corrupted, and clean audio | ✅ Complete | 2025-10-22
| Section 2: Audio preprocessing and error handling | ✅ Complete | 2025-10-22
2025-10-17 | Refactor code so that it will run on local notebooks via pycharm instead of colab | ✅ Complete | 2025-10-22
| Create Section 3: 1. Load the Faster-Whisper model selected from Task 2. 2. Configure inference precision (`float16`, `int8`, etc.) and device (GPU/CPU). 3. Prepare functions to benchmark speed, resource usage, and transcription accuracy. | ✅ Complete | 2025-10-22
| Section 4: Measure transcription speed (real-time factor). - Track CPU / GPU / RAM usage during inference. - Identify optimal configurations for efficiency vs quality. | 🏃 In progress | 2025-10-22
2025-10-21 | Section 4: Measure transcription speed (real-time factor). - Track CPU / GPU / RAM usage during inference. - Identify optimal configurations for efficiency vs quality. | ✅ Complete | 2025-10-22
| Transcribe converted audios with different parameters like beam size 1,2,5 etc and chunk length 10s, 20s etc and save result in json. | ✅ Complete | 2025-10-22
| Preprocess Audio and then transcribe those audios and save result in json | ✅ Complete | 2025-10-22
| Section 6: Visualization, findings, table summary | 🏃 In progress | 2025-10-22
2025-10-22 | Get ground truth transcripts for wer/cer for comparisons for the collected audios | ✅ Complete | 2025-10-22
| Save ground truth transcript into json file in results folder | ✅ Complete | 2025-10-22
| Upload task3_optimization folder on Drive to use it on colab by mounting the Drive content | ✅ Complete | 2025-10-22
| Section 6: Visualization, findings, table summary: Comparison between baseline and enhanced results with the ground truth transcript to find which parameters combination give the lowest wer/cer. | ✅ Complete | 2025-10-22
| Push changes to github for task3 containing everything like raw audio, converted, and preprocessed samples along with .json files having all paramters results. | ✅ Complete | 2025-10-22
2025-10-23 | Understand requirements for task 4 | ✅ Complete | 2025-10-29
| Research about different para in faster whisper to see if the requrements can be satisfied with this model alone | ✅ Complete | 2025-10-29
| Create folders for task 4 and upload it to Drive, Generate mock code to see visually what the end output will look like. | ✅ Complete | 2025-10-29

## Status
Status

## Models
Models/Frameworks | Path | Line # | Code | Column1

## Server
Server